Graphical user interface


Description automatically generated with medium confidenceA red sign with white text

Description automatically generated with low confidence

# Pakistan Floods Response

Situation Report (September 19, 2022)

**Key Figures**



12,860

People Injured

374

Bridges Damaged



## 33 million

People Impacted

## 1,545

People Killed

## 959,819

Livestock Killed

## 1,958,362

Houses Damaged



## 81

Districts Declared ‘Calamity Hit’

## 12,716

KM of Roads Damaged

*Sources: NDMA & UN OCHA*

- - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - -


### The Response

#### Distribution of NFI Kits



Older people and people with disabilities impacted by flooding have improved access to hygiene kits and other non-food items.

#### Dewatering buildings

Support to local government in dewatering rain water from public buildings, including schools, hospitals, Basic Health Units, etc.

#### Distribution of Cash Grants

Older people, people with disabilities and ultra-poor households impacted by flooding have access to lifesaving essentials through multipurpose cash grants.

#### Media Campaigns

Mass-media campaigns in local languages to raise awareness among community members in the most remote areas of Pakistan.



# Flood Response in Jhal Magsi District, Balochistan

### Responding to the urgent needs of at-risk groups, including older people, people with disabilities, and their families in Pakistan

Donor & Lead Agency: **HelpAge International**

Implementing Agency: **Community Development Foundation (CDF)** Project Duration: **August 17 - October 16, 2022** District/Province/Country: **Jhal Magsi, Balochistan, Pakistan** Villages to be covered: **13 villages of Jhal Magsi District**

### Highlights

Flooding washed out the main road to the Jhal Magsi district on August 13, 2022, cutting numerous villages off from the rest of the country. Registration of beneficiaries began on September 4, 2022. Two teams have reached **11 villages and visited 437 households to register older people and people with disabilities and distribute cash and non-food items.**



#### Distribution of Cash Grants

**123** older people, people with disabilities, and ultra-poor households received cash grants, enabling them to access lifesaving essentials.

Total number of beneﬁciaries to be reached: **200**



#### Distribution of NFI Kits

**390** older people and people with disabilities received including hygiene kits and other non-food items.

Total number of beneﬁciaries to be reached: **400**

# Flood Response in Khairpur, Sindh Province

Donor & Lead Agency: **HelpAge International** Implementing Agency: **HANDS**

Project Duration: **1 month** Tehsil: **Khairpur & Kingri**

District/Province/Country: **Khairpur, Sindh, Pakistan**

#### Support to the district government regarding dewatering buildings

HelpAge International is providing support to local government in dewatering rain water from public buildings including schools, hospitals, Basic Health Units, etc. Dewatering will reduce the likelihood of outbreaks of water-borne and vector borne diseases. HelpAge International aims to address accessibility concerns and ensure public buildings are functional and accessible for all, including older people and people with disabilities.

#### Distribution of Non-food Items

HelpAge International distributed **250 kits** with emergency shelter and non-food items to at-risk households. Each kit contains: tarpaulin sheet, bamboo poles, mosquito net, jerry can, bucket, solar lamp, water purification tablets, and rehydration packets.

Total number of beneﬁciaries to be reached: **250**

**Distribution by locality:**

*Hadal Shah Union Council Taluka Kingri*: **57** *Kot Mir Muhammad Union Council Kingri*: **70** *Piryaloi Union Council Kingri*: **63**

*Babarloi Union Council Taluka Khairpur*: **60**

**Ageing and Disability Task Force**

The Pakistan Aging and Disability Task Force (ADTF) has been reactivated. A meeting took place on September 15, 2022, where HelpAge International conﬁrmed to lead the group and hold the secretariat. Meetings will be conducted together with UNHCR, Pakistan Humanitarian Forum (PHF), and the National Humanitarian Network (HNH).